## Component I Subcomponent (a)
Rehabilitation of the Peligre Transmission Line
HA-L1100 and HA-G1030
RESULTS FRAMEWORK
PLURIANNUAL EXECUTING PLAN
| TASK NAME | BUDGET (US$) | DATE |  | Duration
| Task | Grant | start | complete | months
| Component I – Sucomponent (a) Peligre Transmission Line Investment |  | 2015-01-01 | 2018-12-31 | 48
| Supplies and installation of conductors & equipment | 3277275 | 2015-01-01 | 2018-12-31 | 48
| Repairs on towers, supplies and erection of complete towers | 475612 | 2015-01-01 | 2018-12-31 | 48
| Civil works | 472000 | 2015-01-01 | 2018-12-31 | 48
| Geotechnical works | 1305000 | 2015-01-01 | 2018-12-31 | 48
| Underground links | 10021540 | 2015-01-01 | 2018-12-31 | 48
| Substations works | 315000 | 2015-01-01 | 2018-12-31 | 48
| Others (work site mobilization) | 2004331 | 2015-01-01 | 2018-12-31 | 48
| Contingencies | 3216736 | 2015-01-01 | 2018-12-31 | 48
| Subtotal Component I Subcomponent (a) | 21087495 | 2015-01-01 | 2018-01-01 | 48

## Component I Subcomponent (b)
Rehabilitation of the Peligre Transmission Line
HA-L1100 and HA-G1030
RESULTS FRAMEWORK
PLURIANNUAL EXECUTING PLAN
| TASK NAME | BUDGET (US$) | DATE |  | Duration
| Task | Grant | start | complete | months
| Component I - Subcomponent (b) Resettlement and social related impact management |  | 2016-01-01 | 2018-12-31 | 36
| Land acquisition and housing construction costs | 864812 | 2016-01-01 | 2018-12-31 | 36
| Contingencies | 155666 | 2016-01-01 | 2018-12-31 | 36
| Subtotal | 1020478 | 2016-01-01 | 2018-12-31 | 36
Formulas:
DATE = [DATE, row below]
complete = [complete, row below]

## Supervision, adm & management
Rehabilitation of the Peligre Transmission Line
HA-L1100 and HA-G1030
RESULTS FRAMEWORK
PLURIANNUAL EXECUTING PLAN
RESULTS FRAMEWORK
PLURIANNUAL EXECUTING PLAN
ID | TASK NAME | BUDGET (US$) | DATE |  | Duration
| TASK | Total | start | complete | months
| Supervision, administration and management |  | 2015-01-01 | 2018-12-31 | 48
| Supervision works | 1000000 | 2015-01-01 | 2018-12-31 | 48
| Administration and Management | 592028 | 2015-01-01 | 2018-12-31 | 48
| Subtotal | 1592028 | 2015-01-01 | 2018-12-31 | 48
Formulas:
complete = [complete, row above]