## Procurment Plan
Inter-American Development Bank
VPC/FMP
PROCUREMENT PLAN FOR NON-REIMBURSABLE TECHNICAL COOPERATIONS
Country: Regional |  |  |  |  | Executing agency: INE/ENE |  |  |  |  | Public or private sector: (indicate which applies)
Project number: RG-T2608 |  |  |  |  | Title of Project: Scaling up Sustainable Energy for All (SE4ALL) in LAC
Period covered by the plan: 36 Months from date of approval
Threshold for ex-post review of procurements: |  |  |  | Goods and services (in US$):____________ |  | 192000 |  | Consulting services(in US$):____________ | 490000
Item Nº | Ref. AWP | Description (1) | Estimated contract cost (US$) | Procurement Method (2) | Review of procurement (ex-ante or ex-post) (3) | Source of financing and percentage |  | Estimated date of the procurement notice or start of the contract | Technical review by the PTL (4) | Comments
[6 empty] | IDB/MIF % | Local/other %
1 |  | Component 1 - Expansion of SE4ALL in LAC
1.1 |  | Non consulting services
1.1.a |  | 1.1 Support to prepare SE4All target setting | 16000 | PC | ex-post | 100% | 20% | 4Q2015
1.1.b |  | 1.2 TA supporting country priority actions | 5000 | PC | ex-post | 100% | 0% | 4Q2015
1.1.c |  | 1.3 Knowledge Sharing and Communications | 5000 | PC | ex-post | 100% | 0% | 3Q2015
1.2 |  | Consulting services (Individual)
1.2.a |  | 1.1 Support to prepare SE4All target setting | 50000 | IICQ | ex-post | 100% | 20% | 4Q2015
1.2.b |  | 1.2 TA supporting country priority actions | 26000 | IICQ | ex-post | 100% | 0% | 4Q2015
1.2.c |  | 1.3 Knowledge Sharing and Communications | 53000 | IICQ | ex-post | 100% | 0% | 3Q2015
2 |  | Component 2 - Energy Dialogue
2.1 |  | Non consulting services
2.1.a |  | 2.1 Development of a Toolkit for Universal Access Planning | 12000 | PC | ex-post | 100% | 15% | 1Q2016
2.1.b |  | 2.2 Regional Monitoring of SE4All goals in Countries | 4000 | PC | ex-post | 100% | 20% | 3Q2015
2.1.c |  | 2.3 EE Booklets Series | 4000 | PC | ex-post | 100% | 0% | 1Q2016
2.1.d |  | 2.4 Dissemination of knowledge products (workshops and othe dissemination services) | 7000 | PC | ex-post | 100% | 0% | 2Q2016
2.2 |  | Consulting services (Individual)
2.2.a |  | 2.1 Development of a Toolkit for Universal Access Planning | 186000 | IICQ | ex-post | 100% | 15% | 3Q2015
2.2.b |  | 2.2 Regional Monitoring of SE4All goals in Countries | 23000 | IICQ | ex-post | 100% | 20% | 4Q2015
2.2.c |  | 2.3 EE Booklets Series | 1000 | IICQ | ex-post | 100% | 0% | 4Q2015
2.2.d |  | 2.4 Dissemination of knowledge products | 20000 | IICQ | ex-post | 100% | 0% | 3Q2015
3 |  | Component 3 - Operational Support
3.1 |  | Non consulting services
3.1.a |  | 3.1 Support countries in promoting RE projects for financing | 7000 | PC | ex-post | 100% |  | 3Q2015
3.1.b |  | 3.2 Energy Project Preparation Facility | 130000 | PC | ex-post | 100% |  | 2Q2016
|  | 3.2 Design of online tool for virtual marketplace | 3000 | PC | ex-post | 200% |  | 4Q2015
3.1.c |  | 3.3 RE project preparation guide | 2000 | PC | ex-post | 100% |  | 3Q2015
3.2 |  | Consulting services (Individual)
3.2.a |  | 3.1 Support countries in promoting RE projects for financing | 90000 | IICQ | ex-post | 100% |  | 3Q2015
3.2.b |  | 3.2 Energy Project Preparation Facility | 35000 | IICQ | ex-post | 100% |  | 3Q2015
|  | 3.2 Design of online tool for virtual marketplace | 15000 | IICQ | ex-post | 200% |  | 3Q2015
3.2.c |  | 3.3 RE project preparation guide | 6000 | IICQ | ex-post | 100% |  | 3Q2015
0
Total |  |  | 700000 | Prepared by: Csewell |  |  | Date: 6/15/15
(1) Grouping together of similar procurement is recommended, such as computer hardware, publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading, with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) Goods and works: CB: Competitive bidding; PC: Price comparison; DC: Direct contracting.
(2) Consulting firms: CQS: Selection Based on the Consultants' Qualifications; QCBS: Quality and cost-based selection; LCS: Least Cost Selection; FBS: Selection nder a Fixed Budget; SSS: Single Source Selection; QBS: Quality Based selection.
(2) Individual consultants: IICQ: International Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection.
(3) Ex-ante/ex-post review: In general, depending on the institutional capacity and level of risk associated with the procurement, ex-post review is the standard modality. Ex-ante review can be specified for critical or complex process.
(4) Technical review: The PTL will use this column to define those procurement he/she considers "critical"or "complex"that require ex ante review of the terms of reference, technical specifications, reports, outputs, or other items.