## Activities & Timeline
Timeline
59
Comp. | Activity | Cost | 2016 | 2016 | 2017 | 2017 | 2018 | 2018 | 2019 | 2019 | 2020 | 2020
|  | 20000000 | Sem I | Sem II | Sem I | Sem II | Sem I | Sem II | Sem I | Sem II | Sem I | Sem II
| Component 1. Improve student learning outcomes | 11710000
1.1 | Redesign of Curriculum | 5300000
1.1.1 | Purchasing curriculum licenses GRADES 7 and 8 (Math and Language) | 3000000 | x |  | x
1.1.2 | Local adaptation GRADE 7 (Math and Language) | 150000 | x
1.1.3 | Development of textbooks & teacher's guides for GRADE 7 (Science, Art and Culture and Physical Education) | 100000 | x
1.1.4 | Local adaptation GRADE 8 (Math and Language) | 150000 |  |  | x
1.1.5 | Development of textbooks & teacher's guides for GRADE 8 (Science, Art and Culture and Physical Education) | 100000 |  |  | x
1.1.6 | Development of textbooks & teacher's guides for GRADE 4 to 8 (Reading) | 500000 | [6 empty] | x |  | x
1.1.7 | Strategy for improving learning assessment | 500000 |  |  |  |  | x
1.1.8 | Implementing improved learning assessment | 750000 | [6 empty] | x |  | x
1.1.9 | Assessment on gender roles | 50000 |  |  |  |  | x
1.2 | Training and coaching of teachers and school managers on new curriculum | 1610000
1.2.1 | Training and coaching of teachers and school leaders GRADE 7 national implementation (Math and Language) | 200000 |  | x | x
1.2.2 | Training and coaching of teachers and school leaders GRADE 8 national implementation (Math and Language) | 200000 |  |  |  | x | x
1.2.3 | Training and coaching of teachers and school leaders GRADE 7 (Science, Art and Culture and Physical Education) | 200000 |  | x | x
1.2.4 | Training and coaching of teachers and school leaders GRADE 8 (Science, Art and Culture and Physical Education) | 200000 |  |  |  | x | x
1.2.5 | Training and coaching of teachers and school leaders GRADE 4 to 8 (Reading) | 510000 | [6 empty] | x |  | x
1.2.6 | Training and coaching of teachers and school leaders GRADE 1 to 8 (Didactic Material) | 300000 | [6 empty] | x |  | x
1.3 | Providing textbooks and learning materials | 2600000
1.3.1 | Printing textbooks & teacher's guides for GRADE 7 (Math, Language, Science, Art and Culture and Physical Education) | 500000 |  | x
1.3.2 | Printing textbooks & teacher's guides for GRADE 8 (Math, Language, Science, Art and Culture and Physical Education) | 500000 |  |  |  | x
1.3.3 | Printing textbooks & teacher's guides for GRADE 4 to 8 (Reading) | 700000 | [6 empty] | x |  | x
1.3.4 | Purchase Didactic materials for GRADES 1 to 8 | 900000 | [6 empty] | x |  | x
1.4 | Development and delivery of the e-content for primary education | 1000000
1.4.1 | Purchases licenses for e content and software GRADES 3 to 8 (Math and Language) | 900000 | [6 empty] | x |  | x
1.4.2 | Local adaptation GRADES 3 to 8 (Math and Language) | 100000 | [6 empty] | x |  | x
1.5 | Reform of lower secondary | 1200000
1.5.1 | Strategy for reforming lower secondary education | 600000
1.5.2 | Review of curriculum framework, stakeholders consultation and legalize revised curriculum by MOECD | 600000
| Component 2 Increase access to education in the interior and improve facilities at MOESC | 5000000 |  |  |  |  | x
2.1 | Assessment of school infraestructure needs | 500000
2.2 | Rehabilitation of existing schools and teachers housing and construction of new classrooms, media centers and teacher housing in the interior | 3500000 |  |  |  |  | x | x | x | x | x | x
2.3 | Construction of CENASU building | 1000000 | [6 empty] | x |  | x
| Component 3 Improve management at MOESC | 1540000
3.1 | Capacity strengthening of MOECD departments | 300000 |  |  |  |  | x | x | x | x | x | x
3.2 | Social Marketing Campaing | 240000 | x | x | x | x | x | x | x | x | x | x
3.3 | Execution of ICT Policy | 1000000 |  |  |  |  | x | x | x | x | x | x
| Program Administration | 1450000
4.1 | PMU Staff and Operations | 1080000 | x | x | x | x | x | x | x | x | x | x
4.2 | Mid-term and Final Evaluation | 300000 |  |  |  |  | x |  |  | x |  | x
4.3 | Audit (2016-2020) | 70000 | x | x | x | x | x | x | x | x | x | x
| Contingencies | 300000
| TOTAL AMOUNT IN US$ | 20000000
Note on B15: IADB: Should we consider an activity to improve assessment?
Note on C43: Inter-American Development Bank: 50.000 por semestre, por 6 semestres
Note on C44: Inter-American Development Bank: 40,000 per semester, for 6 semesters
Note on C49: Inter-American Development Bank: 180.000 por semestre, 6 semestres

## Disbursements
Disbursement projections per year
Comp. | Activity | Cost | 2016 | 2017 | 2018 | 2019 | 2020
|  | 20000000 | 2928000 | 2928000 | 4103000 | 6563000 | 3478000
|  |  | 14.64% | 14.64% | 20.52% | 32.81% | 17.39%
|  |  | 14.64% | 29.28% | 49.8% | 82.61% | 100%
| Component 1. Improve student learning outcomes | 11710000 | 2650000 | 2650000 | 850000 | 4885000 | 675000
1.1 | Redesign of Curriculum | 5300000
1.1.1 | Purchasing curriculum licenses GRADES 7 and 8 (Math and Language) | 3000000 | 1500000 | 1500000
1.1.2 | Local adaptation GRADE 7 (Math and Language) | 150000 | 150000
1.1.3 | Development of textbooks & teacher's guides for GRADE 7 (Science, Art and Culture and Physical Education) | 100000 | 100000
1.1.4 | Local adaptation GRADE 8 (Math and Language) | 150000 |  | 150000
1.1.5 | Development of textbooks & teacher's guides for GRADE 8 (Science, Art and Culture and Physical Education) | 100000 |  | 100000
1.1.6 | Development of textbooks & teacher's guides for GRADE 4 to 8 (Reading) | 500000 |  |  |  | 500000 | 0
1.1.9 | Strategy for improving learning assessment | 500000 |  |  | 500000
1.1.10 | Implementing improved learning assessment | 750000 |  |  |  | 375000 | 375000
1.1.11 | Assessment on gender roles | 50000 |  |  | 50000
1.2 | Training and coaching of teachers and school managers on new curriculum | 1610000
1.2.1 | Training and coaching of teachers and school leaders GRADE 7 national implementation (Math and Language) | 200000 | 200000
1.2.2 | Training and coaching of teachers and school leaders GRADE 8 national implementation (Math and Language) | 200000 |  | 200000
1.2.3 | Training and coaching of teachers and school leaders GRADE 7 (Science, Art and Culture and Physical Education) | 200000 | 200000
1.2.4 | Training and coaching of teachers and school leaders GRADE 8 (Science, Art and Culture and Physical Education) | 200000 |  | 200000
1.2.5 | Training and coaching of teachers and school leaders GRADE 4 to 8 (Reading) | 510000 |  |  |  | 510000 | 0
1.2.6 | Training and coaching of teachers and school leaders GRADE 1 to 8 (Didactic Material) | 300000 |  |  |  | 300000 | 0
1.3 | Providing textbooks and learning materials | 2600000
1.3.1 | Printing textbooks & teacher's guides for GRADE 7 (Math, Language, Science, Art and Culture and Physical Education) | 500000 | 500000
1.3.2 | Printing textbooks & teacher's guides for GRADE 8 (Math, Language, Science, Art and Culture and Physical Education) | 500000 |  | 500000
1.3.3 | Printing textbooks & teacher's guides for GRADE 4 to 8 (Reading) | 700000 |  |  |  | 700000 | 0
1.3.4 | Purchase Didactic materials for GRADES 1 to 8 | 900000 |  |  |  | 900000 | 0
1.4 | Development and delivery of the e-content for primary education | 1000000
1.4.1 | Purchases licenses for e content and software GRADES 3 to 8 (Math and Language) | 900000 |  |  |  | 900000 | 0
1.4.2 | Local adaptation GRADES 3 to 8 (Math and Language) | 100000 |  |  |  | 100000 | 0
1.5 | Reform of lower secondary | 1200000
1.5.1 | Strategy for reforming lower secondary education | 600000 |  |  | 300000 | 300000 | 0
1.5.2 | Review of curriculum framework, stakeholders consultation and legalize revised curriculum by MOECD | 600000 |  |  |  | 300000 | 300000
| Component 2 Increase access to education in the interior and improve facilities at MOESC | 5000000 | 0 | 0 | 2500000 | 1000000 | 1500000
2.1 | Assessment of school infraestructure needs | 500000 |  |  | 500000
2.2 | Rehabilitation of existing schools and teachers housing and construction of new classrooms, media centers and teacher housing in the interior | 3500000 |  |  | 1000000 | 1000000 | 1500000
2.3 | Construction of CENASU building | 1000000 |  |  | 1000000
| Component 3 Improve management at MOESC | 1540000 | 48000 | 48000 | 448000 | 448000 | 548000
3.1 | Capacity strengthening of MOECD departments | 300000 |  |  | 100000 | 100000 | 100000
3.2 | Social Marketing Campaing | 240000 | 48000 | 48000 | 48000 | 48000 | 48000
3.3 | Execution of ICT Policy | 1000000 |  |  | 300000 | 300000 | 400000
| Program Administration | 1450000 | 230000 | 230000 | 305000 | 230000 | 455000
4.1 | PMU Staff and Operations | 1080000 | 216000 | 216000 | 216000 | 216000 | 216000
4.2 | Mid-term and Final Evaluation | 300000 |  |  | 75000 |  | 225000
4.3 | Audit (2016-2020) | 70000 | 14000 | 14000 | 14000 | 14000 | 14000
| Contingencies | 300000 |  |  |  |  | 300000
| TOTAL AMOUNT IN US$ | 20000000
Note on B16: IADB: Should we consider an activity to improve assessment?
Note on C44: Inter-American Development Bank: 50.000 por semestre, por 6 semestres
Note on C45: Inter-American Development Bank: 40,000 per semester, for 6 semesters
Note on C49: Inter-American Development Bank: 180.000 por semestre, 6 semestres