## TCM Period 2017
|  | Operation Number: |  |  |  | BL-T1087 | [15 empty] | Inter-American Development Bank - IDB
|  | TCM Cycle: |  |  |  | TCM Period 2017
|  | Last Update: |  |  |  | 2017-10-11 13:17
Result Matrix
Outcomes
Outcome: | 1 Increase institutional capacity to identify new areas of export opportunities in Corozal FZ
Indicators |  |  | Flags* |  | Unit of Measure |  |  | Baseline | Baseline Year |  | Means of verification |  |  |  | 2017 | 2018 |  |  | 2019 |  | EOP
1.1 Staff at Ministries and members of the private sector trained in the design of regional export led development policies for Corozal (including the Corozal FZ) and in the modernization of the FZ legal regime |  |  |  |  | Professionals (#) |  |  | 0 | 2017 |  | Workshop participation record |  |  | P | 0 | 40 |  |  | 40 |  | 80
[14 empty] | P(a) | 0 | 40 |  |  | 40 |  | 80
[14 empty] | A | [6 empty] | 0
Outputs: Annual Physical and Financial Progress
1 Export-led Economic Development for the Corozal District | [16 empty] | Physical Progress | [7 empty] | Financial Progress
Outputs |  |  |  | Fund Indicator |  |  | Unit of Measure |  |  | Baseline |  | Baseline Year | Means of Verification |  |  |  |  | 2017 |  | 2018 |  |  | 2019 | EOP |  | 2017 | 2018 |  |  | 2019 |  |  | EOP |  |  | Theme | Flags
1.1 Reports created |  |  |  | Other(RIN) |  |  | # of reports |  |  | 0 |  | 2017 | Report accepted against payment by the Bank |  |  |  | P | 0 |  | 1 |  |  | 0 | 1 | P | 0 | 142500 |  |  | 0 |  |  | 142500 |  |  | Trade
[17 empty] | P(a) | 0 |  | 1 |  |  | 0 | 1 | P(a) | 0 | 142500 |  |  | 0 |  |  | 142500
[17 empty] | A | [7 empty] | A
2 Dissemination workshop | [16 empty] | Physical Progress | [7 empty] | Financial Progress
Outputs |  |  |  | Fund Indicator |  |  | Unit of Measure |  |  | Baseline |  | Baseline Year | Means of Verification |  |  |  |  | 2017 |  | 2018 |  |  | 2019 | EOP |  | 2017 | 2018 |  |  | 2019 |  |  | EOP |  |  | Theme | Flags
2.1 Workshops organized |  |  |  | Other(RIN) Number of workshops delivered |  |  | Workshops (#) |  |  | 0 |  | 2017 | Minutes of workshop |  |  |  | P | 0 |  | 0 |  |  | 1 | 1 | P | 0 | 0 |  |  | 4000 |  |  | 4000 |  |  | Regional Integration
[17 empty] | P(a) | 0 |  | 0 |  |  | 1 | 1 | P(a) | 0 | 0 |  |  | 4000 |  |  | 4000
[17 empty] | A | [7 empty] | A
Other Cost | [25 empty] | 2017 |  |  | 2018 |  |  | 2019 |  |  | Cost
[25 empty] | P | 0 |  |  | 0 |  |  | 3500 |  |  | 3500
Contingencies
[25 empty] | P(a) | 0 |  |  | 0 |  |  | 3500 |  |  | 3500
A
Total Cost | [25 empty] | 2017 |  | 2018 |  |  | 2019 |  |  | Total Cost
[25 empty] | P |  |  | 142500 |  |  | 7500 |  |  | 150000
[25 empty] | P(a) |  |  | 142500 |  |  | 7500 |  |  | 150000
A